## Guidance
Local Transport Delivery Plan Guidance
| Aim | The aim of this template is to gather details of how consolidated funding has been prioritised by the authority over the funding period, with key information on schemes. This guidance should be read alongside the Local Transport Consolidated Funding Settlement Letter and associated annexes
General Instructions
This template should be used to capture the details of how all funding confirmed for the funding period has been prioritised to achieve progress against the indicators in the Local Transport Outcome Framework. To ensure funding is used within the period, LTAs may choose to apply a degree of overprogramming, authorities however remain responsible for any cost overruns to agreed government funding allocations. A single Local Transport Delivery Plan should be completed for the funding period. For authorities receiving ITF and BSF, schemes must each be attributed to one of these pots. Please return as an excel workbook (ie not a pdf or other file format)
Column-by-Column Guidance
| Consolidated Fund (for TIF & BSF ONLY) | This column reflects the two funding pots available to non-MSAs. Authorities should select whether the scheme or intevention will be funded from ITF or BSF. Funding prioritised against each pot must sum to at least the allocations confirmed in settlement letters. Prioritisation of BSF should relate to bus services activity only, and in line with the purposes set out in the Local Transport Consolidated Funding Settlement Letter and accompanying guidance.
| Scheme ID | This column is optional, but can be used to provide any ID used locally to identify schemes. Use a consistent coding convention across all schemes.
| Scheme name or intervention grouping | Include the title of individual scheme or intervention.Substantial and/or complex schemes should be set out separately, but where there are rolling programmes, or groups of smaller scale similar interventions within the same category, these can be grouped together as a package. For grouped interventions, please use a descriptive package name (e.g. highways maintenance).
| Description (include beneficial outcome) | Please provide a short description of the scheme or intervention, including its intended outcome, maximum 250 words. Descriptions will be used to identify schemes with similar purposes (i.e. accessibility), so please use clear and consistent wording. If the scheme or intervention is multimodal, please include reference to the modes included. Some infrastructure schemes may be development only within the funding period (i.e. no construction), this should be noted in the scheme description and reflected in the milestones. As highlighted in the Local Transport Consolidated Funding Settlement Letter, funding is not expected to be used for the purchase of new non-zero emission buses unless there is a compelling operational case - where schemes are expected to involve the purchase of new non-zero emission buses this must be highlighted in the description.
| Mode | Select the mode that best aligns with the scheme or intervention (drop down list in cell, and provided below table). If a scheme is not covered by any of the modal options (e.g. a ferry), select other and ensure that the scheme name and description provides sufficient information to identify the purpose of the scheme. If the scheme is multimodal, ensure all modes are listed in the description field.
| Scheme Category | Select the scheme category from the 15 provided that best aligns with the purpose of the scheme. A drop down list is provided in the cell, with a full list of categories and descriptions below the delivery plan table. Groups of smaller scale similar interventions within the same category only, can be grouped together as a package. Where "other" is selected, please ensure there is sufficient information in the scheme description.
| Location | Please provide a sample postcode for the scheme. Schemes without a fixed location can be marked "LTA-wide".
| Estimated Cost | For each scheme, please include the total estimated costs including across funding sources (government, local or private), together with the contribution from the consolidated funding. Different columns are provided, depending on whether the scheme is funded through capital or revenue. Please provide figures in millions, e.g. for a £3,600,000 scheme, include "3.6".
| Milestones | Please provide estimated high-level delivery milestones for each scheme. For infrastructure schemes, delivery completion should be when scheme is 'open' for the public. For infrastructure expected to be development only within the delivery plan window, delivery milestones can be marked as N/A. For rolling capital programmes expected to be delivery only in the period (e.g. highways maintenance), development milestones can be marked as N/A and delivery milestones covering full funding period if applicable For revenue only schemes without development, development milestones can be marked N/A.
| Retained | Select whether the scheme is expected to meet the criteria to be retained by DfT. Final decisions on scheme retention will be taken by DfT. Schemes that may be considered for retention include individual schemes that: - Have a total cost of £50m, or greater - Interact with or impact the national rail or strategic roads network - Are novel, contentious, or repercussive (including value for money concerns) - Require significant funding beyond the current Spending Review period.

## Local Transport Delivery Plan
| Consolidated Fund | Scheme ID | Scheme name or intervention grouping | Description (include beneficial outcome) | Mode | Scheme Category | Location | Estimated Cost |  |  |  | Milestones |  |  |  | Retained
[8 empty] | Total Estimated Cost REVENUE (£m) | [MTF/ITF/BSF] REVENUE contribution (£m) | Total Estimated Cost CAPITAL (£m) | [MTF/ITF] CAPITAL contribution (£m) | Start Development | Complete Development | Start Delivery | Complete Delivery
Guidance | [For non-MSAs only] Select whether scheme is funded through Integrated Transport Fund (ITF) or Bus Services Fund (BSF) | (If applicable) Any local ID used for identification purposes | Title of individual scheme or intervention. In the case of rolling programmes (e.g. highways maintenance), or groups of smaller scale similar interventions within the same category, these can be grouped together as a package. Substantial and/or complex schemes should be set out separately. | Description/purpose of the scheme or intervention. If the scheme or intervention is multimodal, include reference to what modes and any additional information on the provision provided for each mode. Note whether schemes are development only within the funding period. Schemes involving the potential purchase of new non-zero emission buses must be highlighted in descriptions. (250 words) | Select the modal option that best aligns with the scheme or intervention. If the scheme is multimodal, ensure all modes are listed in the description field. | Select the scheme category that best aligns with the scheme or intervention. | Sample postcode covered by scheme. For inteventions without a fixed location, mark LTA-wide. | For REVENUE schemes, overall cost of the scheme inc. DfT, local funds, private etc | The value of consolidated REVENUE funding allocated towards scheme costs | For CAPITAL schemes, overall cost of the scheme inc. DfT, local funds, private etc | The value of consolidated CAPITAL funding allocated towards scheme costs | Estimated high-level delivery milestones - For infrastructure schemes, delivery completion should be when scheme is 'open' for the public. For infrastructure expected to be development only within the delivery plan window, delivery milestones can be marked as N/A. For revenue only schemes without development, development milestones can be marked N/A. |  |  |  | Do you think this scheme meets the threshold for HMG retention of business case decisions?
Capital | ITF | DOR-8A | ITS upgrades | Signalised crossings, signage or junction maintenance upgrades in some cases incorporating Active Travel improvements, bus. | Multimodal | 8. Road & infrastructure: highways maintenance | LTA Wide | N/A | N/A | 0.9 | 0.9 |  |  | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-2A | School access | Package of school active travel and safety enhancements, including crossings, footways, cycleways school streets and other measures. | Active Travel | 2. Priority and connectivity measures to achieve modal shift | LTA Wide | N/A | N/A | 1.3 | 1.3 |  |  | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-2B | Active travel | Active travel schemes supporting Dorset's Active Travel Infrastructure Plan, including new footways, cycleways linking urban areas and other measures. | Active Travel | 2. Priority and connectivity measures to achieve modal shift | LTA Wide | N/A | N/A | 9.1 | 3.9 |  |  | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-2C | Town centre | Measures to improve active travel access, support bus priority and enhance the public realm through reducing the impact of traffic. | Active Travel | 2. Priority and connectivity measures to achieve modal shift | LTA Wide | N/A | N/A | 0.8 | 0.3 |  |  | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-9A | Safety engineering schemes | Programme of safety improvements on the highway network, including measures to support speed reduction, minor junction re-alignment and rural speed reduction. | Road | 9. Road & infrastructure: improvements, minor enhancements, EV | LTA Wide | N/A | N/A | 2.7 | 2.4 |  |  | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-8B | Bridges & Structures Essential Maintenance | Preventative and reactive maintenance to highway structures, maintaining operation of highway and limiting network disruption. Some works items will be multi-modal (ie including Maritime or Rail). Includes DC funded £1m to Shaftsbury Bridge Refurb and £5.7m to Dinahs Hollow Earthworks/Embankment Reconstruction (2027). | Road | 8. Road & infrastructure: highways maintenance | LTA Wide | N/A | N/A | 16.7 | 10 |  |  | 2026-04-01 | 2030-03-27 | No
Capital | ITF | DOR-8C | Road & infrastructure: highways maintenance | Annual delivery of preventative and planned maintenance treatments to multiple highway assets,including: •Carriageway Resurfacing •Surface Dressing/PSD •SD Patching •Planned patching •Screed Patching •Microasphalt •In Situ Rectcling • Asphalt Rejuvination/Preservation •Cycleway Maintenance •Drainage / Climate Adaptation Works •Footways •Roadmarkings/Catseyes •Landslips •Signs - Strategic/Warning •Road Safety Lining | Road | 8. Road & infrastructure: highways maintenance | LTA wide | N/A | N/A | 127.9 |  |  |  | 2026-04-26 | 2030-03-30
Capital | ITF | DOR-3A | Electrification of Swanage bus fleet | Depot charging infrastructure plus electric buses | Bus | 3. Public Transport: fleet & vehicles | BH19 1HR |  |  | 7.6971 | 4.2171 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2029-12-01 | No
Revenue | BSF | DOR-5A | Enhancements to the CR network | Improvements to the CR network including more frequent services, Saturday services and extra routes. | Bus | 5. Public Transport: new or enhanced routes & services | LTA wide | 2.1336 | 0.89618 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-5B | Enhancements to the commercial bus network | Improvements to the commercial bus network including more frequent services, additional weekend and evening services, and new routes. | Bus | 5. Public Transport: new or enhanced routes & services | LTA wide | 3.6028 | 2.3933 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-5C | Enhanced Community Transport | Improvements to the community transport network | Bus | 5. Public Transport: new or enhanced routes & services | LTA wide | 0.40466 | 0.36572 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-6A | Maintaining the socially necessary Core Route (CR) network | Continued support to maintain the existing network of services. | Bus | 6.Public Transport: existing routes & services | LTA wide | 1.902 | 1.902 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-6B | Maintaining the commercial bus network | Support to maintain service levels where routes are no longer commercially viable | Bus | 6.Public Transport: existing routes & services | LTA wide | 0.78 | 0.78 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Capital | ITF | DOR-1A | RTI and bus stop infrastructure | Improvements to at stop infrastructure | Bus | 1.Interchange, travel hubs, travel stops | LTA wide |  |  | 1.7 | 1.7 | NA | NA | 2026-04-01 | 2030-03-01 | No
Capital | ITF | DOR-7A | Design work on bus capital improvements | Detailed design and delivery prep to provide a pipeline of shovel ready capital schemes | Bus | 7. Public transport & active travel: other infrastructure | LTA wide |  |  | 0.68 | 0.68 |  |  | 2026-04-01 | 2030-03-01 | No
Revenue | BSF | DOR-13A | Capacity and Capability | Provide continued staff resources directly supporting the delivery of the BSIP programme and administration of the EP. | Bus | 13. Back office: delivery & resourcing | NA | 0.282 | 0.282 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-13B | Additional staff resources to speed up delivery | Additional infrastructure/procurement/project management capacity | Bus | 13. Back office: delivery & resourcing | NA | 0.15 | 0.15 |  |  |  |  | 2026-07-01 | 2029-03-01 | No
Revenue | BSF | DOR-14A | Pre-feasibility studies | Early stage scheme development and optioneering | Bus | 14. Back office: development of future proposals or LTPs | LTA wide | 0.15 | 0.15 |  |  |  |  | 2026-04-01 | 2029-03-01 | No
Revenue | BSF | DOR-15A | Participation in YBJ | Monitoring and reporting of bus passenger satisfaction | Bus | 15. Other | LTA wide | 0.21296 | 0.21296 |  |  | NA | NA | 2026-04-01 | 2029-03-01 | No
Revenue | ITF | DOR-13C | Electric Vehicles and Infrastructure - team capacity | Capacity element supporting team delivering continued EV charger rollout across Dorset. | Electric Vehicles & infrastructure | 13. Back office: delivery & resourcing | LTA wide | 0.501 | 0.461 |  |  | 2026-03-01 | 2027-03-01 | 2026-03-01 | 2027-03-01
Revenue | ITF | DOR-14B | Active Travel RDEL - team capacity element | Capacity element supporting team delivering Active Travel pipeline schemes and revenue projects. Enhanced project management capacity for early pipeline schemes to support capital programme delivery | Active Travel | 14. Back office: development of future proposals or LTPs | LTA wide | 0.31 | 0.31 |  |  | 2026-03-01 | 2029-03-01 | 2026-03-01 | 2029-03-01 | No
Revenue | ITF | DOR-2D | Active Travel RDEL - | School streets / active travel engagement and promotions budget. MTO purchase, startup and ongoing revenue support in support of Active Travel schemes (town centre traffic restrictions, school streets etc) | Active Travel | 2. Priority and connectivity measures to achieve modal shift | LTA wide | 0.139 | 0.139 |  |  | 2026-03-01 | 2029-03-01 | 2026-03-01 | 2029-03-01 | No
Revenue | ITF | DOR-14C | LTG RDEL | Enhanced Capacity and Capability Support for Transport Planning, Project Management to deliver incresed capital programme elements | Multimodal | 14. Back office: development of future proposals or LTPs | LTA Wide | 0.47 | 0.47 |  |  | 2026-03-01 | 2029-03-01 | 2026-03-01 | 2029-03-01 | No
Revenue | ITF | DOR-14D | LTG RDEL | Specialist support to wider programme from Transport Modelling, procurement etc | Multimodal | 14. Back office: development of future proposals or LTPs | LTA Wide | 0.305 | 0.305 |  |  | 2026-03-01 | 2029-03-01 | 2026-03-01 | 2029-03-01 | No
Revenue | ITF | DOR-14E | LTG RDEL | Project support with National Highways for A35 scheme development | Road | 14. Back office: development of future proposals or LTPs | Dorchester | 0.15 | 0.15 |  |  | 2026-03-01 | 2029-03-01 | 2026-03-01 | 2029-03-01
Mode |  | Scheme types | Scheme type descriptions
Active Travel |  | 1. Interchanges, travel hubs, travel stops | Hub, interchange, Park & Ride, station, stops and shelters for bus or tram, floating bus stop upgrades, accessibility upgrades
Bus |  | 2. Priority and connectivity measures to achieve modal shift | bus gates and bus lanes, signal priority; traffic reduction measures; footways & footbridges, segregated cycle lanes, school streets
Electric Vehicles & infrastructure |  | 3. Public Transport: fleet & vehicles | Rolling stock, vehicles, new buses & trams, retrofits, zero-emission fleet or fleet upgrades, vehicles for Demand Responsive Transport, onboard accessibility upgrades (eg wheelchair spaces), onboard CCTV, onboard displays & audio-visual info
Rail |  | 4. Public Transport: fares & ticketing | Fare capping, youth offers, discretionary concessionary schemes, integrated ticketing, multi-operator ticketing, accessible fares
Motor traffic incl. Highways Asset |  | 5. Public Transport: new or enhanced routes & services | New routes for bus or tram, timetable enhancements, Demand Responsive Transport (DRT) routes
Tram / light rail |  | 6.Public Transport: existing routes & services | Service support for existing routes for bus or tram, or Demand Responsive Transport (DRT)
Multimodal |  | 7. Public transport & active travel: other infrastructure | Cycle parking, e-bikes, depots, layover facilities, infrastructure and power supply for ZEBs, tramlines. (Please put EV buses in category 3).
Other (e.g. maritime) |  | 8. Road & infrastructure: highways maintenance | Potholes, road maintenance, verges, highways asset improvements, road signage, lighting, drop kerbs
|  | 9. Road & infrastructure: improvements, minor enhancements, EV | Road improvements to include junction realignment, junction signalisation, adding or altering roundabouts, traffic calming and speed enforcement , road safety measures. EV infrastructure, including chargepoints, pavement channels, grid upgrades, adaptations for fleet vehicles
|  | 10. Road & infrastructure: major maintenance & enhancements projects | New or replacement bridges, tunnels, roads, bypasses, other major structures; dualling; top-ups to schemes funded from other sources (e.g. MRN)
|  | 11. Digital, data and technology | Contactless readers, ticket machines; back-office systems, development of apps
|  | 12. Information and marketing | Branding & marketing, public information, info points, journey planning tools, promotional campaigns
|  | 13. Back office: delivery & resourcing | Staffing, admin, consultancy, operational, capability & capacity spend (C&C), programme management, training
|  | 14. Back office: development of future proposals or LTPs | Development only', research, evaluation, feasibility studies, business case development, LTPs (Local Transport Plans)
|  | 15. Other | Please give as much information as possible under 'scheme description', so that we can categorize appropriately.

## Sign-off
Declaration (to be completed by the LTA s151/s73 officer)
I confirm that all the information provided within this report is accurate and that all material detail has been disclosed. I also confirm that funding has been allocated for the purposes set out in the Local Transport Funding Settlement Letter [and MoU when provided] and in line with the authority's legal duties for best value, propriety, regularity, and that the programme represents value for money. I confirm that the authority has: • Applied management controls to mitigate the risk of fraud and corruption; • Applied management controls to ensure funding will be used in accordance with UK subsidy control legislation; • Applied management controls to ensure that any procurement undertaken by a Contracting Authority using funds will comply with public procurement regulations; • Complied with its obligations under the Public Sector Equality Duty; • Complied with the requirements under the General Data Protection Regulations.
Name | Sean Cremer
Role | Corporate Director - Finance and Commercial (S151 Officer)
Signature

## Data Validation (hidden)
Consolidated fund | Mode | Scheme types | Scheme type descriptions | Funding | Retained
ITF | Active Travel | 1. Interchanges, travel hubs, travel stops | Hub, interchange, Park & Ride, station, stops and shelters for bus or tram, floating bus stop upgrades, accessibility upgrades | Revenue | Yes
BSF | Bus | 2. Priority and connectivity measures to achieve modal shift | bus gates and bus lanes, signal priority; traffic reduction measures; footways & footbridges, segregated cycle lanes, school streets | Capital | No
| Electric Vehicles & infrastructure | 3. Public Transport: fleet & vehicles | Rolling stock, vehicles, new buses & trams, retrofits, zero-emission fleet or fleet upgrades, vehicles for Demand Responsive Transport, onboard accessibility upgrades (eg wheelchair spaces), onboard CCTV, onboard displays & audio-visual info |  | Unsure
| Rail | 4. Public Transport: fares & ticketing | Fare capping, youth offers, discretionary concessionary schemes, integrated ticketing, multi-operator ticketing, accessible fares
| Road | 5. Public Transport: new or enhanced routes & services | New routes for bus or tram, timetable enhancements, Demand Responsive Transport (DRT) routes
| Tram / light rail | 6.Public Transport: existing routes & services | Service support for existing routes for bus or tram, or Demand Responsive Transport (DRT)
| Multimodal | 7. Public transport & active travel: other infrastructure | Cycle parking, e-bikes, depots, layover facilities, infrastructure and power supply for ZEBs, tramlines. (Please put EV buses in category 3).
| ‘Back office’ | 8. Road & infrastructure: highways maintenance | Potholes, road maintenance, verges, highways asset improvements, road signage, lighting, drop kerbs
| Other (e.g. maritime) | 9. Road & infrastructure: improvements, minor enhancements, EV | Road improvements to include junction realignment, junction signalisation, adding or altering roundabouts, traffic calming and speed enforcement , road safety measures. EV infrastructure, including chargepoints, pavement channels, grid upgrades, adaptations for fleet vehicles
|  | 10. Road & infrastructure: major maintenance & enhancements projects | New or replacement bridges, tunnels, roads, bypasses, other major structures; dualling; top-ups to schemes funded from other sources (e.g. MRN)
|  | 11. Digital, data and technology | Contactless readers, ticket machines; back-office systems, development of apps
|  | 12. Information and marketing | Branding & marketing, public information, info points, journey planning tools, promotional campaigns
|  | 13. Back office: delivery & resourcing | Staffing, admin, consultancy, operational, capability & capacity spend (C&C), programme management, training
|  | 14. Back office: development of future proposals or LTPs | Development only', research, evaluation, feasibility studies, business case development, LTPs (Local Transport Plans)
|  | 15. Other | Please give as much information as possible under 'scheme description', so that we can categorize appropriately.